## Release Dates
Month | Release Date
January | 2020-01-30
February | 2020-02-27
March | 2020-03-26
April | 2020-04-30
May | 2020-05-28
June | 2020-06-25
July | 2020-07-30
August | 2020-08-27
September | 2020-09-24
October | 2020-10-22
November | 2020-11-19
December | 2020-12-17

## Definitions
Administrative Tasks |  | Cases |  | Misc
Enhancements for (Month's) Release must be entered in Salesforce | Integrator team must have the enhancement request for a given month entered by this deadline. The given month will be removed from the picklist following this deadline. | Build Completion Due - Case for Deployment to UAT must be submitted by EOD | In addition to development being completed, packages you wish to deploy should have been fully tested in your developer SIT environment. DTC STRONGLY recommends you complete development well before this deadline to leave time for sufficient testing. When you check in to your enhancement branch in Github, package will also be deployed to ENTSD, which is a shared environment where you can have elevated access for additional testing if requested, DTC will not be completing your pre and post deployment steps in this environment but STRONGLY RECOMMENDS you do so. Following testing in your developer SIT environment (and ENTSD), submit a case to move to UAT no later than this deadline - for June forward, your package will also need to be merged in to your merge branch in advance of this deadline and case submission. | DTC Review Period | DTC will be reviewing your package components and pre- and post-deployment steps in this period. If we are unable to complete steps they will be returned to you with questions. This will also allow time for the deployment team to resolve any build errors. If you change your deployment plan after this date, there is no guarantee it will be completed (unless submitted with one of the two redeployment requests), the original deployment plan (or lack thereof) will be used for the first deployment, please abide by the submission deadline for build completion.
User Stories must be attached to the Enhancement in Salesforce | Integrator team must have user stories written and attached to their enhancement request by the end of the day on the listed deadline. | Case for Re-Deployment (of fixes)to UAT …. | There are two deadlines for redeployment of fixes to UAT. These will be the only opportunities to redeploy to UAT as we must keep the environment stable enough for others to test at the other times. You must have your completed package merged in to your merge branch prior to the listed deadline. If you have deployment plan updates, they must also be uploaded to your enhancement requests prior to the deadline, please do not delete your old plan, and please highlight the differences. Once these items are complete, submit your redeployment case, also before the listed deadline. | First Day UAT will be available after refresh | This is the first day UAT will be available to receive deployments. Due to time constraints surrounding refreshes, we will not be able to deploy packages to UAT prior to this date. If you have a special circumstance, please attend a DTC call to discuss.
User Setup Information Due | User setup instructions should be submitted to the DTC team for the setup of users in test and staging environments. A case requesting setup should also be submitted. Please see User Info Template for more information. | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) | Following developer validation and Business Owner sign off in UAT, submit a case for deployment to Staging. Please DO NOT submit this case prior to receiving Business Owner Sign off in UAT. All testing and validation as well as case submission must occur by this deadline. Should your package fail to deploy to UAT and you have a new submission with changes, you MUST submit a new case. | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Following collection of UAT changes for re-deployment (one re-deployment attempt), code freeze will be in effect. Your changes will be deployed to UAT then you will have a few days to finalize business owner sign off. Your package will then be deployed to Staging and teams given the opportunity to validate, though no additional changes may be made. If at this point you determine you are not ready for Production, your package may be pulled from the release and pushed to the next month.
|  | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Following developer validation in Staging, submit a case for deployment to Production. Please DO NOT submit this case prior to validating in Staging. All testing and validation as well as case submission must occur by this deadline. | Staging will be available for testing after 2PM EST | The first deployment attempt to Staging will begin at 11AM EST on Monday. If there are no issues with the deployment, DTC anticipates changes will be available for testing/training by 2PM EST Tuesday. Be advised, any conflicts within the package that cause the deployment to fail could push the ready time back. A Chatter update will be posted when Staging is available.
|  |  |  | Next Release Push to Prod | Deployments to Prod will begin at approximately 5PM EST. A Chatter update will be posted when the deployment to Prod has been completed.
Business Owner Sign Offs |  | DTC Maintenance
Business Owner Sign off on User Stories Due | Sign off from the business owner indicating they have reviewed and approved the user stories should be attached to the enhancement request or chattered in the feed on the enhancement request. This should occur no later than the end of the day on the listed deadline. | Refresh UAT& ENTSD | Established date for DTC to begin refreshing the listed environments. Environments are typically not available for use until 2-3 days after this process begins. Please plan your migrations and trainings accordingly. | Resource Chatter Groups
Business Owner Sign off on UAT Due | Sign off from the business owner indicating they have tested in UAT (and the functionality matches the user stories they previously sign off on) should be attached to the enhancement request or chattered in the feed on the enhancement request. This should occur no later than the end of the day on the listed deadline. | Refresh Staging | Established date for DTC to begin refreshing the Staging environment. Staging is typically not available for up to 7 days after this process begins. Please plan your migrations and trainings accordingly. | For the most up to date deployment and schedule information, please join the following: | VA Deployment, VA System Integrators, VA Salesforce Developers, VA Projects Technical Design
Business Owner Sign off for (Month's) Production Release Due before 2PM | Sign off from the business owner indicating they have tested in Prod (and the functionality matches the user stories and UAT testing they previously sign off on) should be attached to the enhancement request or chattered in the feed on the enhancement request. This should occur no later than the end of the day on the listed deadline. | Holiday | DTC will be closed for the Federal Holiday listed. No deployments or cases will be worked.

## Calendar (hidden)
2020 | January
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | Indicates Administrative Task Deadline
| Enhancements for January Release must be entered in Salesforce | New Year's Day |  | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Case Submission Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates the Code Freeze period
2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | DTC Scheduled Refresh
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates a Federal Holiday, DTC will not be working
2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | Indicates next push to Production
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | UAT/Staging environment available following deployment
2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26
Martin Luther King Jr Day |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-02-03 | 2020-02-04 | Notes:
Business Owner Sign off for August Production Release Due before 2PM
2020 | February
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23
President's Day |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-03-02 | 2020-03-03 | Notes:
2020 | March
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | Refresh UAT& ENTSD
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce
2020-03-30 | 2020-03-31 | Notes:
2020 | April
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05
User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-05-04 | 2020-05-05 | Notes:
2020 | May
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-17
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31
Memorial Day | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
Code Freeze |  |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-06-01 | 2020-06-02 | Notes:
2020 | June
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20 | 2020-06-21
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27 | 2020-06-28
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | Refresh UAT& ENTSD
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce
2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05
User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
2020-07-06 | 2020-07-07 | Notes:
2020 | July
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05
|  |  | User Stories must be attached to the Enhancement in Salesforce | Independence Day (Observed) | Independence Day
Business Owner Sign off on User Stories Due
2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-08-03 | 2020-08-04 | Notes:
2020 | August
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-08-31 | 2020-09-01 | Notes:
2020 | September
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13
Labor Day | DTC Review Period |  | UAT will be available for testing after 2PM EST | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-10-05 | 2020-10-06 | Notes:
2020 | October
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18
Columbus Day |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-11-02 | 2020-11-03 | Notes:
2020 | November
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15
| Case for Re-Deployment (of fixes)to UAT must be submitted by 3PM | Veterans Day | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29
|  |  | Thanksgiving Day | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-11-30 | 2020-12-01 | Notes:
DTC Review Period
2020 | December
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27
Christmas Day
2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03
2021-01-04 | 2021-01-05 | Notes:

## January
2020 | January
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | Indicates Administrative Task Deadline
| Enhancements for January Release must be entered in Salesforce | New Year's Day |  | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Case Submission Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates the Code Freeze period
2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | DTC Scheduled Refresh
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates a Federal Holiday, DTC will not be working
December Retrospective at 10AM ET
2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | Indicates next push to Production
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | UAT/Staging environment available following deployment
2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26
Martin Luther King Jr Day |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-02-03 | 2020-02-04 | Notes:
Business Owner Sign off for August Production Release Due before 2PM

## February
2020 | February
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | Indicates Administrative Task Deadline
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Case Submission Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates the Code Freeze period
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD |  |  | DTC Scheduled Refresh
2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | Indicates a Federal Holiday, DTC will not be working
|  | January Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates next push to Production
2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | UAT/Staging environment available following deployment
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM | Salesforce Spring '20 Release Live in Production 12AM EDT! | Check status.salesforce.com for details, our Production org is NA21
2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23
President's Day |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Enhancements for March Release must be entered in Salesforce |  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-03-02 | 2020-03-03 | Notes:

## March
2020 | March
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | Indicates Administrative Task Deadline
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Case Submission Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates the Code Freeze period
| Code Freeze |  |  | Refresh UAT& ENTSD |  |  | DTC Scheduled Refresh
2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | Indicates a Federal Holiday, DTC will not be working
|  | February Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates next push to Production
2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | UAT/Staging environment available following deployment
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | Refresh UAT& ENTSD
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce
2020-03-30 | 2020-03-31 | Notes:

## April
2020 | April
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | Indicates Administrative Task Deadline
|  | March Retrospective at 1PM ET |  | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Case Submission Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates the Code Freeze period
2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | DTC Scheduled Refresh
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates a Federal Holiday, DTC will not be working
2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | Indicates next push to Production
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | UAT/Staging environment available following deployment
2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-05-04 | 2020-05-05 | Notes:

## May
2020 | May
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03 | Indicates Administrative Task Deadline
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Case Submission Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates the Code Freeze period
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD |  |  | DTC Scheduled Refresh
2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10 | Indicates a Federal Holiday, DTC will not be working
|  | April Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates next push to Production
2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-17 | UAT/Staging environment available following deployment
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31
Memorial Day | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
Code Freeze |  |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-06-01 | 2020-06-02 | Notes:

## June
2020 | June
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07 | Indicates Administrative Task Deadline
|  | May Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Case Submission Deadline
2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14 | Indicates the Code Freeze period
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM | Salesforce Summer '20 Release Live in Production 12AM EDT! | Check status.salesforce.com for details, our Production org is NA21 | DTC Scheduled Refresh
2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20 | 2020-06-21 | Indicates a Federal Holiday, DTC will not be working
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | Indicates next push to Production
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | UAT/Staging environment available following deployment
2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27 | 2020-06-28
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | Refresh UAT& ENTSD
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce
2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05
User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
2020-07-06 | 2020-07-07 | Notes:

## July
2020 | July
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05 | Indicates Administrative Task Deadline
|  | June Retrospective at 1PM ET | User Stories must be attached to the Enhancement in Salesforce | Independence Day (Observed) | Independence Day |  | Indicates Case Submission Deadline
|  |  | Business Owner Sign off on User Stories Due |  |  |  | Indicates the Code Freeze period
2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12 | DTC Scheduled Refresh
|  |  | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates a Federal Holiday, DTC will not be working
2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19 | Indicates next push to Production
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | UAT/Staging environment available following deployment
2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-08-03 | 2020-08-04 | Notes:

## August
2020 | August
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02 | Indicates Administrative Task Deadline
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Case Submission Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates the Code Freeze period
| Code Freeze |  | Enhancements for February Release must be entered in Salesforce | Refresh UAT& ENTSD |  |  | DTC Scheduled Refresh
2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | Indicates a Federal Holiday, DTC will not be working
|  | July Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates next push to Production
2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | UAT/Staging environment available following deployment
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-08-31 | 2020-09-01 | Notes:

## September
2020 | September
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | Indicates Administrative Task Deadline
|  | August Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Case Submission Deadline
2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | Indicates the Code Freeze period
Labor Day | DTC Review Period |  | UAT will be available for testing after 2PM EST | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | DTC Scheduled Refresh
2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | Indicates a Federal Holiday, DTC will not be working
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | Indicates next push to Production
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | UAT/Staging environment available following deployment
2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04
|  | September Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-10-05 | 2020-10-06 | Notes:

## October
2020 | October
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | Indicates Administrative Task Deadline
|  | September Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Case Submission Deadline
2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | Indicates the Code Freeze period
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | DTC Scheduled Refresh
2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | Indicates a Federal Holiday, DTC will not be working
Columbus Day |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | Indicates next push to Production
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) | Salesforce Winter '21 Release Live in Production 12AM EDT! | Check status.salesforce.com for details, our Production org is NA21 | UAT/Staging environment available following deployment
2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01
|  | October Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-11-02 | 2020-11-03 | Notes:

## November
2020 | November
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | Indicates Administrative Task Deadline
|  | October Retrospective at 1PM ET | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Case Submission Deadline
2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | Indicates the Code Freeze period
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | DTC Scheduled Refresh
2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | Indicates a Federal Holiday, DTC will not be working
| Case for Re-Deployment (of fixes)to UAT must be submitted by 3PM | Veterans Day | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | Indicates next push to Production
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | UAT/Staging environment available following deployment
2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29
| November Retrospective at 1PM ET |  | Thanksgiving Day | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
2020-11-30 | 2020-12-01 | Notes:
DTC Review Period

## December
2020 | December
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Indicates Business Owner Sign off Deadline
2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06 | Indicates Administrative Task Deadline
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | Indicates Case Submission Deadline
2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13 | Indicates the Code Freeze period
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | DTC Scheduled Refresh
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | Indicates a Federal Holiday, DTC will not be working
2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | Indicates next push to Production
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | UAT/Staging environment available following deployment
Business Owner Sign off on User Stories Due
| Code Freeze |  | Enhancements for next Release must be entered in Salesforce | Refresh UAT& ENTSD
2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27
Christmas Day
2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03
2021-01-04 | 2021-01-05 | Notes:
December Retrospective at 1PM ET