## Release Dates
Month | Release Date
January | 2019-01-31
February | 2019-02-28
March | 2019-03-28
April | 2019-04-25
May | 2019-05-23
June | 2019-06-27
July | 2019-07-25
August | 2019-08-29
September | 2019-09-26
October | 2019-10-24
November | 2019-11-21
December | 2019-12-19

## Definitions
Administrative Tasks |  | Cases |  | Misc
Enhancements for (Month's) Release must be entered in Salesforce | Integrator team must have the enhancement request for a given month entered by this deadline. The given month will be removed from the picklist following this deadline. | Build Completion Due - Case for Deployment to UAT must be submitted by EOD | In addition to development being completed, packages you wish to deploy should have been fully tested in your developer SIT environment. DTC STRONGLY recommends you complete development well before this deadline to leave time for sufficient testing. When you check in to your enhancement branch in Github, package will also be deployed to ENTSD, which is a shared environment where you can have elevated access for additional testing if requested, DTC will not be completing your pre and post deployment steps in this environment but STRONGLY RECOMMENDS you do so. Following testing in your developer SIT environment (and ENTSD), submit a case to move to UAT no later than this deadline - for June forward, your package will also need to be merged in to your merge branch in advance of this deadline and case submission. | DTC Review Period | DTC will be reviewing your package components and pre- and post-deployment steps in this period. If we are unable to complete steps they will be returned to you with questions. This will also allow time for the deployment team to resolve any build errors. If you change your deployment plan after this date, there is no guarantee it will be completed (unless submitted with one of the two redeployment requests), the original deployment plan (or lack thereof) will be used for the first deployment, please abide by the submission deadline for build completion.
User Stories must be attached to the Enhancement in Salesforce | Integrator team must have user stories written and attached to their enhancement request by the end of the day on the listed deadline. | Case for Re-Deployment (of fixes)to UAT …. | There are two deadlines for redeployment of fixes to UAT. These will be the only opportunities to redeploy to UAT as we must keep the environment stable enough for others to test at the other times. You must have your completed package merged in to your merge branch prior to the listed deadline. If you have deployment plan updates, they must also be uploaded to your enhancement requests prior to the deadline, please do not delete your old plan, and please highlight the differences. Once these items are complete, submit your redeployment case, also before the listed deadline. | First Day UAT will be available after refresh | This is the first day UAT will be available to receive deployments. Due to time constraints surrounding refreshes, we will not be able to deploy packages to UAT prior to this date. If you have a special circumstance, please attend a DTC call to discuss.
User Setup Information Due | User setup instructions should be submitted to the DTC team for the setup of users in test and staging environments. A case requesting setup should also be submitted. Please see User Info Template for more information. | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) | Following developer validation and Business Owner sign off in UAT, submit a case for deployment to Staging. Please DO NOT submit this case prior to receiving Business Owner Sign off in UAT. All testing and validation as well as case submission must occur by this deadline. Should your package fail to deploy to UAT and you have a new submission with changes, you MUST submit a new case. | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Following collection of UAT changes for re-deployment (one re-deployment attempt), code freeze will be in effect. Your changes will be deployed to UAT then you will have a few days to finalize business owner sign off. Your package will then be deployed to Staging and teams given the opportunity to validate, though no additional changes may be made. If at this point you determine you are not ready for Production, your package may be pulled from the release and pushed to the next month.
|  | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Following developer validation in Staging, submit a case for deployment to Production. Please DO NOT submit this case prior to validating in Staging. All testing and validation as well as case submission must occur by this deadline. | Staging will be available for testing after 2PM EST | The first deployment attempt to Staging will begin at 11AM EST on Monday. If there are no issues with the deployment, DTC anticipates changes will be available for testing/training by 2PM EST Tuesday. Be advised, any conflicts within the package that cause the deployment to fail could push the ready time back. A Chatter update will be posted when Staging is available.
|  |  |  | Next Release Push to Prod | Deployments to Prod will begin at approximately 5PM EST. A Chatter update will be posted when the deployment to Prod has been completed.
Business Owner Sign Offs |  | DTC Maintenance
Business Owner Sign off on User Stories Due | Sign off from the business owner indicating they have reviewed and approved the user stories should be attached to the enhancement request or chattered in the feed on the enhancement request. This should occur no later than the end of the day on the listed deadline. | Refresh UAT& ENTSD | Established date for DTC to begin refreshing the listed environments. Environments are typically not available for use until 2-3 days after this process begins. Please plan your migrations and trainings accordingly. | Resource Chatter Groups
Business Owner Sign off on UAT Due | Sign off from the business owner indicating they have tested in UAT (and the functionality matches the user stories they previously sign off on) should be attached to the enhancement request or chattered in the feed on the enhancement request. This should occur no later than the end of the day on the listed deadline. | Refresh Staging | Established date for DTC to begin refreshing the Staging environment. Staging is typically not available for up to 7 days after this process begins. Please plan your migrations and trainings accordingly. | For the most up to date deployment and schedule information, please join the following: | VA Deployment, VA System Integrators, VA Salesforce Developers, VA Projects Technical Design
Business Owner Sign off for (Month's) Production Release Due before 2PM | Sign off from the business owner indicating they have tested in Prod (and the functionality matches the user stories and UAT testing they previously sign off on) should be attached to the enhancement request or chattered in the feed on the enhancement request. This should occur no later than the end of the day on the listed deadline. | Holiday | DTC will be closed for the Federal Holiday listed. No deployments or cases will be worked.

## January
2019 | January
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2018-12-31 | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | 2019-01-06
Last iSIT/UAT Refresh was 12/24/2018 | New Year's Day | Enhancements for January Release must be entered in Salesforce |  | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Business Owner Sign off Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates Administrative Task Deadline
2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13
First Day iSITDTC will be available for use |  |  | User Setup Information Due | Build Completion Due - Case for Deployment to iSIT must be submitted by EOD |  |  | Indicates Case Submission Deadline
2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20
|  | Case for Deployment to UAT must be submitted by EOD |  |  |  |  | Indicates the Code Freeze period
2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-27
Martin Luther King Jr Day |  |  |  | Business Owner Sign off on UAT Due | Code freeze - Begins EOD Friday - No additional changes will be accepted |  | DTC Scheduled Refresh
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | Indicates a Federal Holiday, DTC will not be working
2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31 | 2019-02-01 | 2019-02-02 | 2019-02-03
Staging will be available for testing after 2PM EST |  | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates next push to Production
|  |  | Enhancements for February Release must be entered in Salesforce | Business Owner Sign off on User Stories Due for February
Refresh iSIT & UAT& ENTSD
2019-02-04 | 2019-02-05 | Notes:
Business Owner Sign off for January Production Release Due before 2PM

## February
2019 | February
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31 | 2019-02-01 | 2019-02-02 | 2019-02-03
Staging will be available for testing after 2PM EST |  | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Business Owner Sign off Deadline
|  |  | Enhancements for February Release must be entered in Salesforce | Business Owner Sign off on User Stories Due |  |  | Indicates Administrative Task Deadline
Refresh iSIT & UAT& ENTSD
2019-02-04 | 2019-02-05 | 2019-02-06 | 2019-02-07 | 2019-02-08 | 2019-02-09 | 2019-02-10 | Indicates Case Submission Deadline
Business Owner Sign off for January Production Release Due before 2PM | First Day iSITDTC will be available for use |  | User Setup Information Due | Build Completion Due - Case for Deployment to iSIT must be submitted by EOD | Salesforce Spring '19 Release Live in Production 12AM EDT! | Check status.salesforce.com for details, our Production org is NA21
2019-02-11 | 2019-02-12 | 2019-02-13 | 2019-02-14 | 2019-02-15 | 2019-02-16 | 2019-02-17 | Indicates the Code Freeze period
Case for Deployment to UAT must be submitted by EOD
2019-02-18 | 2019-02-19 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-23 | 2019-02-24 | DTC Scheduled Refresh
President's Day |  |  |  | Business Owner Sign off on UAT Due | Code freeze - Begins EOD Friday - No additional changes will be accepted |  | Indicates a Federal Holiday, DTC will not be working
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-02 | 2019-03-03 | Indicates next push to Production
Staging will be available for testing after 2PM EST |  | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
|  |  | Enhancements for March Release must be entered in Salesforce | Refresh iSIT & UAT& ENTSD
2019-03-04 | 2019-03-05
Business Owner Sign off for February Production Release Due before 2PM | First Day iSITDTC will be available for use

## March
2019 | March
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-02 | 2019-03-03
Staging will be available for testing after 2PM EST |  | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Business Owner Sign off Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates Administrative Task Deadline
|  |  | Enhancements for March Release must be entered in Salesforce | Refresh iSIT & UAT& ENTSD
2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-09 | 2019-03-10 | Indicates Case Submission Deadline
Business Owner Sign off for February Production Release Due before 2PM | First Day iSITDTC will be available for use |  | User Setup Information Due | Build Completion Due - Case for Deployment to iSIT must be submitted by EOD
Refresh Staging/Prod Mirror
2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | Indicates the Code Freeze period
Case for Deployment to UAT must be submitted by EOD
2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 | DTC Scheduled Refresh
|  |  |  | Business Owner Sign off on UAT Due | Code freeze - Begins EOD Friday - No additional changes will be accepted |  | Indicates a Federal Holiday, DTC will not be working
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | Indicates next push to Production
Staging will be available for testing after 2PM EST |  | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
|  |  | Enhancements for April Release must be entered in Salesforce | Refresh iSIT & UAT& ENTSD
2019-04-01 | 2019-04-02
Business Owner Sign off for March Production Release Due before 2PM | First Day iSITDTC will be available for use

## April
2019 | April
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07
Business Owner Sign off for March Production Release Due before 2PM | First Day iSITDTC will be available for use |  | User Setup Information Due | Build Completion Due - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Business Owner Sign off Deadline
2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | Indicates Administrative Task Deadline
UAT will be available for testing after 2PM EST |  |  |  | Case for Re-Deployment (of fixes)to UAT must be submitted by EOD | Code freeze - Begins EOD Friday - No additional changes will be accepted
2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | Indicates Case Submission Deadline
UAT will be available for testing after 2PM EST |  | Code freeze |  | Business Owner Sign off on UAT Due | Code freeze
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | Indicates the Code Freeze period
2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28
Staging will be available for testing after 2PM EST |  | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | DTC Scheduled Refresh
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates a Federal Holiday, DTC will not be working
|  |  | Enhancements for May Release must be entered in Salesforce | Refresh UAT& ENTSD
2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | Indicates next push to Production
Business Owner Sign off for April Production Release Due before 2PM |  | First Day UAT will be available after refresh | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD

## May
2019 | May
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05
Business Owner Sign off for April Production Release Due before 2PM |  | First Day UAT will be available after refresh | User Setup Information Due | Build Completion Due - Case for Deployment to UAT must be submitted by EOD |  |  | UAT/Staging environment available following deployment
|  |  |  | Refresh Staging/Prod Mirror |  |  | Indicates Business Owner Sign off Deadline
2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12 | Indicates Administrative Task Deadline
DTC Review Period |  | UAT will be available for testing after 2PM EST
2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | Indicates Case Submission Deadline
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | Indicates the Code Freeze period
2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26
Code Freeze | Staging will be available for testing after 12PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | Refresh UAT& ENTSD |  |  | DTC Scheduled Refresh
| Code Freeze | [5 empty] | Indicates a Federal Holiday, DTC will not be working
2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02
Memorial Day | Enhancements for June Release must be entered in Salesforce | Staging/ProdMirror Refresh Previously scheduled on this date moved to 5/3 |  | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates next push to Production
Business Owner Sign off on User Stories Due

## June
2019 | June
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02
Memorial Day | Enhancements for June Release must be entered in Salesforce |  |  | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Business Owner Sign off Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates Administrative Task Deadline
2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-08 | 2019-06-09
Business Owner Sign off for May Production Release Due before 2PM |  | First Day UAT will be available after refresh | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Case Submission Deadline
2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | 2019-06-15 | 2019-06-16
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM | Salesforce Summer '19 Release Live in Production 12AM EDT! | Check status.salesforce.com for details, our Production org is NA21 | Indicates the Code Freeze period
2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | DTC Scheduled Refresh
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | Indicates a Federal Holiday, DTC will not be working
2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-06-29 | 2019-06-30
Code Freeze | Staging will be available for testing after 2PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates next push to Production
| Code Freeze |  |  | Business Owner Sign off on User Stories Due
|  |  | Enhancements for July Release must be entered in Salesforce | Refresh UAT& ENTSD |  |  | UAT/Staging environment available following deployment
2019-07-01 | 2019-07-02
Business Owner Sign off for June Production Release Due before 2PM

## July
2019 | July
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07
Business Owner Sign off for June Production Release Due before 2PM |  | First Day UAT will be available after refresh | Independence Day | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Business Owner Sign off Deadline
|  |  |  | User Setup Information Due |  |  | Indicates Administrative Task Deadline
2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | Indicates Case Submission Deadline
2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-20 | 2019-07-21
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | Indicates the Code Freeze period
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | DTC Scheduled Refresh
Code Freeze | Staging will be available for testing after 2PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | Refresh UAT& ENTSD |  |  | Indicates a Federal Holiday, DTC will not be working
Code Freeze
2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | Indicates next push to Production
Enhancements for August Release must be entered in Salesforce |  |  |  | User Stories must be attached to the Enhancement in Salesforce |  |  | UAT/Staging environment available following deployment
Business Owner Sign off for July Production Release Due before 2PM |  |  |  | Business Owner Sign off on User Stories Due

## August
2019 | August
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04
Enhancements for August Release must be entered in Salesforce |  |  |  | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Business Owner Sign off Deadline
Business Owner Sign off for July Production Release Due before 2PM |  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates Administrative Task Deadline
2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11
|  | First Day UAT will be available after refresh | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Case Submission Deadline
2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM |  |  | Indicates the Code Freeze period
2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | DTC Scheduled Refresh
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | Indicates a Federal Holiday, DTC will not be working
2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31 | 2019-09-01
Code Freeze | Staging will be available for testing after 2PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates next push to Production
| Code Freeze |  |  | Business Owner Sign off on User Stories Due
|  |  | Enhancements for September Release must be entered in Salesforce | Refresh UAT& ENTSD |  |  | UAT/Staging environment available following deployment
2019-09-02 | 2019-09-03
Labor Day | Business Owner Sign off for August Production Release Due before 2PM

## September
2019 | September
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31 | 2019-09-01
Staging will be available for testing after 2PM EST |  | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates Business Owner Sign off Deadline
|  |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates Administrative Task Deadline
Refresh UAT& ENTSD
2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | Indicates Case Submission Deadline
Labor Day | Business Owner Sign off for August Production Release Due before 2PM | First Day UAT will be available after refresh | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD
Refresh Staging/Prod Mirror
2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | Indicates the Code Freeze period
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | DTC Scheduled Refresh
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | Indicates a Federal Holiday, DTC will not be working
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | Indicates next push to Production
Code Freeze | Staging will be available for testing after 2PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | UAT/Staging environment available following deployment
| Code Freeze |  |  | Business Owner Sign off on User Stories Due
|  |  | Enhancements for October Release must be entered in Salesforce | Refresh UAT& ENTSD
2019-09-30 | 2019-10-01
Business Owner Sign off for September Production Release Due before 2PM

## October
2019 | October
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06
Business Owner Sign off for September Production Release Due before 2PM |  | First Day UAT will be available after refresh | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Business Owner Sign off Deadline
2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | Indicates Administrative Task Deadline
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM | Salesforce Winter '20 Release Live in Production 12AM EDT! | Check status.salesforce.com for details, our Production org is NA21
2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | Indicates Case Submission Deadline
Columbus Day |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 3PM | Code freeze - Begins 3PM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | Indicates the Code Freeze period
2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27
Code Freeze | Staging will be available for testing after 2PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | DTC Scheduled Refresh
| Code Freeze |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates a Federal Holiday, DTC will not be working
|  |  | Enhancements for November Release must be entered in Salesforce | Refresh UAT& ENTSD
2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-03 | Indicates next push to Production
Business Owner Sign off for October Production Release Due before 2PM |  | First Day UAT will be available after refresh | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | UAT/Staging environment available following deployment

## November
2019 | November
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-03
Business Owner Sign off for October Production Release Due before 2PM |  | First Day UAT will be available after refresh | User Setup Information Due | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | Indicates Business Owner Sign off Deadline
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | Indicates Administrative Task Deadline
DTC Review Period |  | UAT will be available for testing after 2PM EST |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 12 PM - Deployment to kick off at 3PM
2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | Indicates Case Submission Deadline
Veterans Day |  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze
|  |  |  | Case for Deployment to Staging must be submitted by EOD (after receiving sign off) |  |  | Indicates the Code Freeze period
2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-24
Code Freeze | Staging will be available for testing after 2PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | User Stories must be attached to the Enhancement in Salesforce |  |  | DTC Scheduled Refresh
| Code Freeze |  |  | Business Owner Sign off on User Stories Due |  |  | Indicates a Federal Holiday, DTC will not be working
|  |  | Enhancements for December Release must be entered in Salesforce | Refresh UAT& ENTSD
2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | Indicates next push to Production
Business Owner Sign off for November Production Release Due before 2PM |  | First Day UAT will be available after refresh | Thanksgiving Day | Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD |  |  | UAT/Staging environment available following deployment
User Setup Information Due
2019-12-02 | 2019-12-03

## December
2019 | December
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01
Business Owner Sign off for November Production Release Due before 2PM |  | First Day UAT will be available after refresh | Thanksgiving Day | User Setup Information Due |  |  | Indicates Business Owner Sign off Deadline
2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08
| Build Completion Due (code must be merged in Merge Branch) - Case for Deployment to UAT must be submitted by EOD | DTC Review Period |  | UAT will be available for testing after 2PM EST |  |  | Indicates Case Submission Deadline
2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15
|  | Case for Re-Deployment (of fixes)to UAT must be submitted by 9 AM | Code freeze - Begins 9AM Wednesday - No additional changes will be accepted | Business Owner Sign off on UAT Due | Code Freeze |  | Indicates the Code Freeze period
Case for Deployment to Staging must be submitted by EOD (after receiving sign off)
2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | DTC Scheduled Refresh
Code Freeze | Staging will be available for testing after 2PM EST | Case for Deployment to Production should be submitted by EOD Certifying Enhancement is Prod ready | Next Release Push to Prod | Refresh UAT& ENTSD |  |  | Indicates a Federal Holiday, DTC will not be working
2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29
Enhancements for January 2020 Release must be entered in Salesforce | Refresh Staging/Prod Mirror | Christmas Day |  | User Stories must be attached to the Enhancement in Salesforce |  |  | Indicates next push to Production
|  |  |  | Business Owner Sign off on User Stories Due |  |  | UAT/Staging environment available following deployment
2019-12-30 | 2019-12-31