## Calendar
2020 | January
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05
DTC Copado Development Period - 1-on-1 with Copado Team (Zach/Aditya unavailable for all other tasks)
2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12
DTC Copado Development Period - 1-on-1 with Copado Team (Zach/Aditya unavailable for all other tasks)
2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19
DTC Copado Development Period - 1-on-1 with Copado Team (Zach/Aditya unavailable for all other tasks) |  | Integrator Mandatory Copado Training Period (finish Copado Academy, work with DTC during Office Hours) - runs in parallel with current deployment cycle/process
2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26
Integrator Mandatory Copado Training Period (finish Copado Academy, work with DTC during Office Hours) - runs in parallel with current deployment cycle/process
2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02
Integrator Mandatory Copado Training Period (finish Copado Academy, work with DTC during Office Hours) - runs in parallel with current deployment cycle/process
2020 | February
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02
Integrator Mandatory Copado Training Period (finish Copado Academy, work with DTC during Office Hours) - runs in parallel with current deployment cycle/process
2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09
Integrator Mandatory Copado Training Period (finish Copado Academy, work with DTC during Office Hours) - runs in parallel with current deployment cycle/process
2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16
Integrator Mandatory Copado Training Period (finish Copado Academy, work with DTC during Office Hours) - runs in parallel with current deployment cycle/process
2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23
President's Day | Questions/Clarification Period Tailored to March Release
2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01
Questions/Clarification Period Tailored to March Release |  | DTC Current February Release Process Freeze |  | Integrator Shift to Copado Cut Over Date (Including Refresh of DTC Envs)
2020-03-02 | 2020-03-03 | Notes:
2020 | March
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01
Questions/Clarification Period Tailored to March Release |  | DTC Current February Release Process Freeze |  | Integrator Shift to Copado Cut Over Date (Including Refresh of DTC Envs)
2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08
Intregrator Copado Implementation/Support -- Refresh Sandboxes and begin ENTSD Deployments |  |  |  | Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15
Intregrator Copado Implementation/Support -- ENTSD Deployment Support |  |  |  | Push to UAT will occur EOD - all code must be in final state - case for UAT deployment and final deployment plan must be submitted
2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22
DTC Review Period |  | UAT will be available for testing after 2PM EST
2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29
Case for Deployment to Staging must be submitted by 9am | Staging will be available for testing after 12PM EST |  | Next Release Push to Prod | Integrator and DTC Copado Retro
2020-03-30 | 2020-03-31 | Notes:
2020 | April
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05
Intregrator Copado Implementation/Support -- Refresh Sandboxes and begin ENTSD Deployments
2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12
Intregrator Copado Implementation/Support -- ENTSD Deployment Support |  |  |  | Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19
| Push to UAT will occur EOD - all code must be in final state - case for UAT deployment and final deployment plan must be submitted | DTC Review Period
2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26
DTC Review Period | UAT will be available for testing after 2PM EST - note: if available UAT will be released as early as possible |  |  | Case for Deployment to Staging must be submitted by EOD- User stories moving forward should be marked "Ready to Promote." Stories not moving forward should have their org credential changed back to your dev box
2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03
| Staging will be available for testing after 12PM EST |  | Next Release Push to Prod
2020-05-04 | 2020-05-05 | Notes:
2020 | May
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03
DTC to begin back promotion to SIT sandboxes from April User Stories in Staging |  |  | April Release Push to Prod after 5PM EST | User Stories for May must be attached to the Enhancement in Salesforce
Business Owner Sign off on User Stories Due
2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10
Intregrator Copado Implementation/Support -- Sandbox alignment and ENTSD Deployment Support |  |  |  | May Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-17
| Push to UAT will occur EOD - all code must be in final state - case for UAT deployment and final deployment plan must be submitted | DTC Review/Deployment Period -- Please ensure your team has resources available for any deployment error troubleshooting needed
2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24
DTC Review/Deployment Period | UAT will be available for testing after 2PM EST - note: if available UAT will be released as early as possible |  | Enhancement for June must be entered in Salesforce | Business Owner Sign off on UAT Due
Case for Deployment to Staging must be submitted by EOD- User stories moving forward should be marked "Ready to Promote." Stories not moving forward be moved to DO NOT USE release, and have the "exclude from CBM" checkbox checked
2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31
Memorial Day |  | Staging will be available for testing after 12PM EST | May Release Push to Prod after 5PM EST | User Stories for June must be attached to the Enhancement in Salesforce
| DTC to begin back promotion to SIT sandboxes from May User Stories in Staging |  |  | Business Owner Sign off on User Stories Due
2020-06-01 | 2020-06-02 | Notes:
2020 | June
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07
Intregrator Copado Implementation/Support -- Sandbox alignment and ENTSD Deployment Support |  |  |  | June Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14
| Push to UAT will occur EOD - all code must be in final state - case for UAT deployment and final deployment plan must be submitted | DTC Review/Deployment Period -- Please ensure your team has resources available for any deployment error troubleshooting needed
2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20 | 2020-06-21
DTC Review/Deployment Period | UAT will be available for testing after 2PM EST - note: if available UAT will be released as early as possible |  | Enhancements for July Release must be entered in Salesforce | Business Owner Sign off on UAT Due
Case for Deployment to Staging must be submitted by EOD- User stories moving forward should be marked "Ready to Promote." Stories not moving forward be moved to DO NOT USE release, and have the "exclude from CBM" checkbox checked
2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27 | 2020-06-28
| Staging will be available for testing after 12PM EST |  | June Release Push to Prod
DTC to begin back promotion to SIT sandboxes from June User Stories in Staging
2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05
Intregrator Copado Implementation/Support -- Sandbox alignment and ENTSD Deployment Support |  |  | User Stories for July must be attached to the Enhancement in Salesforce | Intregrator Copado Implementation/Support -- Sandbox alignment and ENTSD Deployment Support
Business Owner Sign off on July User Stories Due
2020-07-06 | 2020-07-07 | Notes:
2020 | July
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05
Intregrator Copado Implementation/Support -- Sandbox alignment and ENTSD Deployment Support |  |  | User Stories for July must be attached to the Enhancement in Salesforce | Independence Day (Observed) | Independence Day
Business Owner Sign off on July User Stories Due
2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12
Intregrator Copado Implementation/Support -- Sandbox alignment and ENTSD Deployment Support |  |  |  | July Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19
| Push to UAT will occur EOD - all code must be in final state - case for UAT deployment and final deployment plan must be submitted | DTC Review/Deployment Period -- Please ensure your team has resources available for any deployment error troubleshooting needed
2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26
DTC Review/Deployment Period | UAT will be available for testing after 2PM EST - note: if available UAT will be released as early as possible |  | Enhancements for August Release must be entered in Salesforce | Business Owner Sign off on UAT Due
Case for Deployment to Staging must be submitted by EOD- User stories moving forward should be marked "Ready to Promote." Stories not moving forward be moved to DO NOT USE release, and have the "exclude from CBM" checkbox checked
2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02
| Staging will be available for testing after 12PM EST |  | July Release Push to Prod | User Stories for August must be attached to the Enhancement in Salesforce
DTC to begin back promotion to SIT sandboxes from July User Stories in Staging |  |  |  | Business Owner Sign off on August User Stories Due
2020-08-03 | 2020-08-04 | Notes:
2020 | August |  |  | NOTE: DTC has only committed to the following deadlines in this release month, the other deadlines such as the UAT availability will be added as we continue to receive lessons learned from prior releases.
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02
|  |  | July Release Push to Prod | User Stories for August must be attached to the Enhancement in Salesforce
Business Owner Sign off on August User Stories Due
2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09
August Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16
2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23
Enhancements for September Release must be entered in Salesforce
2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30
|  |  | August Release Push to Prod | User Stories for September must be attached to the Enhancement in Salesforce
Business Owner Sign off on September User Stories Due
2020-08-31 | 2020-09-01 | Notes:
2020 | September |  |  | NOTE: DTC has only committed to the following deadlines in this release month, the other deadlines such as the UAT availability will be added as we continue to receive lessons learned from prior releases.
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06
September Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13
Labor Day
2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20
Enhancements for October Release must be entered in Salesforce
2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27
|  |  | September Release Push to Prod | User Stories for October must be attached to the Enhancement in Salesforce
Business Owner Sign off on October User Stories Due
2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04
October Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-10-05 | 2020-10-06 | Notes:
2020 | October |  |  | NOTE: DTC has only committed to the following deadlines in this release month, the other deadlines such as the UAT availability will be added as we continue to receive lessons learned from prior releases.
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04
October Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11
2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18
Columbus Day |  |  |  | Enhancements for November Release must be entered in Salesforce
2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25
|  |  | October Release Push to Prod | User Stories for November must be attached to the Enhancement in Salesforce
Business Owner Sign off on November User Stories Due
2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01
November Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-11-02 | 2020-11-03 | Notes:
2020 | November |  |  | NOTE: DTC has only committed to the following deadlines in this release month, the other deadlines such as the UAT availability will be added as we continue to receive lessons learned from prior releases.
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01
November Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08
2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15
|  | Veterans Day |  | Enhancements for December Release must be entered in Salesforce
2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22
|  |  | November Release Push to Prod | User Stories for December must be attached to the Enhancement in Salesforce
Business Owner Sign off on December User Stories Due
2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29
|  |  | Thanksgiving Day | December Build Completion Due (code must be merged or questions on merging must be submitted to DTC) -- deployment plan submission is also required
2020-11-30 | 2020-12-01 | Notes:
2020 | December |  |  | NOTE: DTC has only committed to the following deadlines in this release month, the other deadlines such as the UAT availability will be added as we continue to receive lessons learned from prior releases.
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06
2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13
Enhancements for January Release must be entered in Salesforce
2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20
December Release Push to Prod
2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27
Christmas Day
2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03
2021-01-04 | 2021-01-05 | Notes: