## Calendar
2022 | January
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02
|  | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET | New Years Day Observed --- The DTC will not be available on this Federal Holiday
2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC will make INT available for deployments by 5PM ET
2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23
Birthday of Martin Luther King Jr. --- The DTC will not be available on this Federal Holiday. |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-01-31 | 2022-02-01 | Notes:
2022 | February
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13
Washington's Birthday --- The DTC will not be available on this Federal Holiday. |  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06
2022-03-07 | 2022-03-08 | Notes:
2022 | March
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06
DTC Maintenance Period (Gov Cloud Migration)
2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-04-04 | 2022-04-05 | Notes:
2022 | April
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03
2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-05-02 | 2022-05-03 | Notes:
2022 | May
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01
2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC will make INT available for deployments by 12PM ET
2022-05-30 | 2022-05-31 | Notes:
2022 | June
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05
Memorial Day --- The DTC will not be available on this Federal Holiday. |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25 | 2022-06-26
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-07-04 | 2022-07-05 | Notes:
2022 | July
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03
2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10
Independence Day --- The DTC will not be available on this Federal Holiday. |  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31
DTC Maintenance Period
2022-08-01 | 2022-08-02 | Notes:
2022 | August
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-09-05 | 2022-09-06 | Notes:
2022 | September
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04
2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11
Labor Day --- The DTC will not be available on this Federal Holiday. |  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-10-03 | 2022-10-04 | Notes:
2022 | October
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02
2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC will make INT available for deployments by 5PM ET
2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16
Columbus Day --- The DTC will not be available on this Federal Holiday. |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-10-31 | 2022-11-01 | Notes:
2022 | November |  |  | Note: The deployment dates for November and December are subject to change. Any changes will be announced no later than August 2022.
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle | Veterans Day --- The DTC will not be available on this Federal Holiday.
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | Thanksgiving Day --- The DTC will not be available on this Federal Holiday. | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04
2022-12-05 | 2022-12-06 | Notes:
2022 | December |  |  | Note: The deployment dates for November and December are subject to change. Any changes will be announced no later than August 2022.
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11
DTC will make INT available for deployments by 12PM ET |  | Integration Deployment and Deployment Plan Due - Deployment plan must be attached to the Enhancement and user stories in INT must be in final state by 11:59PM ET | DTC Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in a future cycle
|  | Ready to Promote box Checked in Copado --- Promote to Regression box checked on ENH request by 11:59PM ET |  | Regression and Staging will be available for testing after 5PM ET - note: if possible both environments will be released as early as possible (Steps will be completed as soon as possible)
2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18
|  | Promote to Prod box checked on ENH; User Stories marked as Ready to Promote; RTM for REG and/or Staging attached by 11:59PM ET | Production release at 5PM ET --- Final Business owner approval due one week from this date | RTM for the next release must be attached to the Enhancement in Salesforce by 11:59PM ET
|  | Go/No Go decision for User Stories must be made by 4PM ET | All Enhancements for the next Prod release must be entered in Salesforce by 11:59PM ET | Architecture Design and all related Security Risks must be approved by 5PM ET
DTC to kick off INT refresh by 2 PM ET --- Available Monday
2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25
2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | 2023-01-01
Christmas Day --- The DTC will not be available on this Federal Holiday.
2023-01-02 | 2023-01-03 | Notes: