## Calendar
Indicates SI Milestone Progress - | Start |  |  |  | End
Indicates DTC Milestone Progress- | Start |  |  |  | End
Indicates BO Go/No-Go Decision-
2023 | January
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | 2023-01-01
|  |  | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
(DTC) INT Sandbox to be made available by 2PM ET
(SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08
New Years Day (Observed) - DTC will not be available on this Federal Holiday |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" by 11:59 PM ET | (DTC) Production release at 5PM ET --- Final Business owner approval due one week from this date | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (DTC) INT Sandbox to be made available by 2PM ET
(SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22
Birthday of Martin Luther King, Jr. - DTC will not be available on this Federal Holiday |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
2023-01-30 | 2023-01-31 | Notes:
2023 | February
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26
Washington’s Birthday- DTC will not be available on this Federal Holiday |  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05
2023-03-06 | 2023-03-07 | Notes:
2023 | March
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-04-03 | 2023-04-04 | Notes:
2023 | April
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02
2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30
Maintenance Period 1
2023-05-01 | 2023-05-02 | Notes:
2023 | May
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (DTC) INT Sandbox to be made available by 2PM ET
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04
Memorial Day - DTC will not be available on this Federal Holiday |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-06-05 | 2023-06-06 | Notes:
2023 | June
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04
2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25
Juneteenth National Independence Day - DTC will not be available on this Federal Holiday |  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-07-03 | 2023-07-04 | Notes:
2023 | July
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02
2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09
| Independence Day - DTC will not be available on this Federal Holiday | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-29 | 2023-07-30
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-07-31 | 2023-08-01 | Notes:
2023 | August
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-05 | 2023-08-06
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-26 | 2023-08-27
Maintenance Period 2
2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-09-04 | 2023-09-05 | Notes:
2023 | September
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03
2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-10
Labor Day - DTC will not be available on this Federal Holiday |  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-10-02 | 2023-10-03 | Notes:
2023 | October
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01
2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (DTC) INT Sandbox to be made available by 2PM ET
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15
Columbus Day - DTC will not be available on this Federal Holiday |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-10-30 | 2023-10-31 | Notes:
2023 | November
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle | Veteran Day (Observed) - DTC will not be available on this Federal Holiday
(SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET
2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19
(DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle |  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
(DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful) |  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | DTC to kick off INT refresh (ALL Salesforce Orgs) by 2 PM ET --- Available Monday
(SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26
Maintenance Period 3 |  |  | Thanksgiving Day - DTC will not be available on this Federal Holiday | Maintenance Period 3
2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-12-04 | 2023-12-05 | Notes:
2023 | December
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03
2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date | (SI) RTM and Business Owner Sign off for lower environments submitted to ENH by 11:59 PM ET
|  | (BO) Go/No Go decision for User Stories must be made by 4PM ET | (SI) All Enhancements Requests for following Production release are due by 11:59 PM ET | (SI) Architecture Design and Sec Risks must be approved by 5 PM ET
2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17
(DTC) INT Sandbox to be made available by 12PM ET |  | (SI) INT Deployment Completed and Deployment Plan Attached to ENH - Code is frozen - 11:59 PM ET | (DTC) Review/Deployment Period (REG and Staging) -- Teams with errors will be removed from the package and pushed in the next cycle
|  | (SI) User Story marked "Ready to Promote" --- ENH marked "Promote to REG & Staging" by 11:59 PM ET |  | (DTC) Regression and Staging Deployments will be completed by 5PM ET --- (Steps will start as soon as deployemnts are successful)
2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24
|  | (SI) Reg/Staging RTM and Sign off attached to ENH --- User Stories marked "Ready to Promote" and ENH marked "Promote to Prod" | (DTC) Production release at 5PM ET --- (SI) Final Business owner approval due one week from this date
(BO) Go/No Go decision for User Stories must be made by 4PM ET
2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31
Christmas Day - DTC will not be available on this Federal Holiday
2024-01-01 | 2024-01-02 | Notes: